## Sheet1
Project Communication Plan Template
taskford.com
Project Name: Spring 2025 Marketing Campaign |  | Project Manager: Jennie Doe |  | Start Date: Jan 15, 2025 | End Date: Jun 30, 2025
Project Objectives: - Goal 1: Keep stakeholders informed on project progress with weekly updates. - Goal 2: Ensure timely approvals from the client for all marketing materials. - Goal 3: Facilitate collaboration between the creative, marketing, and sales teams to launch campaigns smoothly.
Communication Schedule
Task | Date/Time | Owner | Audience | Purpose
Weekly Project Update Email | Every Monday, 9 AM | Jennie Doe | All stakeholders | Inform stakeholders of the week's progress.
Creative Feedback Meeting | Every other Wednesday, 11 AM | Emily Green | Creative Team, PM | Review and approve creative content.
Campaign Progress Report | Every Friday, 4 PM | Sarah White | Marketing Team, PM | Track KPIs, update team on campaign progress.
Client Check-In Call | 1st Monday of each month, 10 AM | Jennie Doe | Client | Review campaign status, gather feedback.
Sales Sync Call | Every other Thursday, 2 PM | Mike Brown | Sales Team, PM | Share updates on marketing efforts and product info.