## Construction Plan Template
CONSTRUCTION PROJECT PLAN TEMPLATE
PROJECT TITLE |  |  | START | END
PROJECT MANAGER |  |  | PROJECT DURATION IN DAYS
TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
Planning | In Progress | Ben | 2025-06-01 | 2025-06-15 | 15
Demo Prep | Not Started | Annie | 2025-06-01 | 2025-06-15 | 15
Demolition | Complete | Lucas | 2025-06-03 | 2025-06-10 | 8
Excavation | On Hold | Joey | 2025-06-03 | 2025-06-11 | 9
Concrete | In Progress | Liam | 2025-06-05 | 2025-06-12 | 8
Pre backfill | Complete | Peter | 2025-06-15 | 2025-06-29 | 15
Framing | In Progress | Kent | 2025-06-16 | 2025-06-29 | 14
Roof | Needs Review
Plumbing | Needs Review
Windows | On Hold
HVAC | Not Started
Electrical | Not Started
A/V | In Progress
House wrap | In Progress
Insulation | On Hold
Drywall | In Progress
Exterior stone | In Progress
Exterior case work | In Progress
Laundry/furnace room flooring | In Progress
Hardwoods | In Progress
Tile | In Progress
Cabinets | In Progress
Plumbing -hang sinks | In Progress
Interior doors | In Progress
Millwork | In Progress
Interior painting | In Progress
Stone Counters | In Progress
Schedule Buffer | In Progress
Decks | In Progress
Interior doors- hang & hardware | In Progress
Appliances | In Progress
Plumbing | In Progress
Electrical | In Progress
Bathroom Glass | In Progress
Garage Door dress up | In Progress
FINAL Inspections | In Progress
Wrap up | Not Started
House Cleaning | In Progress
Complete | In Progress
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Status Key - DO NOT DELETE
STATUS KEY - DO NOT DELETE
STATUS KEY
Not Started
In Progress
Complete
On Hold
Overdue
Needs Review