## Template
https://taskford.com/en
Budget Tracking Report Template
Example: The Mobile Banking App project requires strict financial oversight due to its $500,000 budget. This report tracks spending for the first three months and is shared with the CFO.
Section | Field | Description/Input
Project Information | Project Name | Mobile Banking App Development
| Report Date | 2025-06-13
| Project Manager | Sarah Johnson
Budget Overview | Category | Labor
| Planned Budget | 150000
| Actual Spend | 155000
| Variance | 5000
| % Variance | 3.33%
| Category | Software Licenses
| Planned Budget | 50000
| Actual Spend | 52000
| Variance | 2000
| % Variance | 4%
| Category | Testing Services
| Planned Budget | 100000
| Actual Spend | 102000
| Variance | 2000
| % Variance | 2%
Forecast | Projected Spend | $510,000 (for entire project)
Commentary | Variance Explanation | Labor costs exceeded due to overtime for API integration delays.
| Corrective Actions | Reduce overtime; renegotiate vendor contract.
Customization Tips:
Create a bar chart in Excel for planned vs. actual spend.
Highlight variances >5% with conditional formatting.
Add a notes column for stakeholder comments.