## Template
https://taskford.com/en
Monthly Project Progress Report Template
Example: The Mobile Banking App project is in its third month. This monthly progress report is prepared for executive stakeholders (e.g., CEO, CFO) to provide a high-level overview of progress, risks, and budget status.
Section | Field | Description/Input
Project Information | Project Name | Mobile Banking App Development
| Report Month | 2025-06-01
| Project Manager | Sarah Johnson
Executive Summary | Key Metrics | 60% complete, 3% over budget, 2 high-priority risks
| Summary | On schedule for Q3 launch; user authentication module nearly complete. Vendor delays impacting progress.
Progress Update | Tasks Completed | - Completed login and registration modules - Conducted 20 user tests - Designed payment UI
| Milestones Achieved | - Phase 2 (Core Features) 80% complete
| % Complete | 60%
Risk Register | Risk Description | - Vendor API delays - Potential security vulnerabilities
| Status | - In progress (vendor meeting scheduled) - Mitigation plan drafted
Budget Overview | Planned Budget | $300,000 (for first 3 months)
| Actual Spend | 309000
| Variance | $9,000 (3%)
Next Steps | Upcoming Milestones | - Complete payment module - Begin beta testing
Customization Tips:
- Create a Gantt chart in Excel to show timeline progress.
- Use conditional formatting to highlight budget variances >5%.