## Template
https://taskford.com/en
Project Closure Report Template
Example: The Mobile Banking App project has reached completion after six months. This closure report is shared with all stakeholders to summarize outcomes and lessons learned.
Section | Field | Description/Input
Project Information | Project Name | Mobile Banking App Development
| Report Date | 2025-09-30
| Project Manager | Sarah Johnson
Project Summary | Objectives | Develop a secure, user-friendly mobile banking app by Q3 2025.
| Outcomes | App launched on 09/25/2025; 95% user satisfaction in beta testing.
Performance Metrics | On-Time Delivery | 98% (slight delay due to final testing)
| Budget Performance | $510,000 spent vs. $500,000 budgeted (2% over)
Lessons Learned | Key Lessons | - Vendor delays require backup plans - Early security testing is critical
| Process Improvements | - Implement automated testing - Improve vendor contract terms
Stakeholder Feedback | Feedback Summary | “App is intuitive and secure” (Client); “Testing phase was thorough” (Users).
| Satisfaction Metrics | 95% stakeholder approval; 4.8/5 user rating
Customization Tips:
Add a pie chart for satisfaction metrics.
Include a column for stakeholder-specific comments.
Add an archiving section for deliverables.