## Template
https://taskford.com/en
Risk and Issue Report Template
Example: The Mobile Banking App project faces risks due to its reliance on third-party vendors and strict compliance requirements. This report is used in steering committee meetings to track and resolve risks.
Section | Field | Description/Input
Project Information | Project Name | Mobile Banking App Development
| Report Date | 2025-06-13
| Project Manager | Sarah Johnson
Risk Log | Risk ID | R001
| Risk Description | Delay in API delivery from third-party vendor
| Likelihood | High
| Impact | Medium
| Mitigation Strategy | Engage backup vendor; escalate to vendor’s management
| Status | Open
| Risk ID | R002
| Risk Description | Potential security vulnerabilities in authentication module
| Likelihood | Medium
| Impact | High
| Mitigation Strategy | Conduct penetration testing; hire external security consultant
| Status | In Progress
Issue Tracker | Issue ID | I001
| Issue Description | Server downtime during testing
| Responsible Party | IT Team
| Deadline | 2025-06-20
Summary | New Risks This Period | 1 new risk (R002) identified
Customization Tips:
Add a risk matrix chart in Excel (likelihood vs. impact).
Use color-coding for status (e.g., red for “Open”).