## Template
https://taskford.com/en
Weekly Status Report Template
Example: For the Mobile Banking App project, the team is in Sprint 3 (Week 6) of development, focusing on user authentication features. This weekly status report is shared with stakeholders (e.g., product owner, CTO) to provide a snapshot of progress.
Section | Field | Description/Input
Project Information | Project Name | Mobile Banking App Development
| Report Date | 2025-06-13
| Project Manager | Sarah Johnson
Executive Summary | Summary | Sprint 3 on track; completed 80% of user authentication module. Minor delay in API integration.
Progress Update | Tasks Completed | - Developed login screen (80% complete)
- Implemented two-factor authentication
- Conducted 5 user tests
| Milestones Achieved | - Sprint 3 backlog 70% cleared
Risks and Blockers | Blockers/Risks | - API integration delayed due to third-party vendor issues
| Proposed Solutions | - Schedule urgent meeting with vendor
- Explore alternative API provider
Next Steps | Upcoming Tasks | - Finalize login module
- Start payment module development
- Plan Sprint 4
Notes | Additional Comments | Stakeholder review meeting scheduled for 06/20/2025.
Customization Tips:
- Add a “Status” column with conditional formatting (e.g., green for “On Track,” red for “At Risk”).
- Insert a progress bar chart in Excel for tasks completed.
- Include your company logo in the header.